## LUMP SUM QUOTE FORM
5. LUMP SUM QUOTE FORM
reference weighing
Item | Description | Unit | Estimated Quantity | Materials & Equipment | Manpower |  | Construcion Equipment | Total | Weighing for certification | Rules of credit/ Comments
|  |  |  | USD | HH | USD | USD | USD
1 | Engineering | [7 empty] | 10%
1.1 | Detail Engineering
1.1.1 | Detail Engineering for Permits | LS | 1 | [5 empty] | 40% | Progress by issuance according to document list, 70% Rev. A and 100% Rev. 0 approved by the Company; HH for each doc
1.1.2 | Engineering route survey from HPF to HCP | LS | 1 | [5 empty] | 50%
1.1.3 | Engineering route survey from HCP to HSP | LS | 1
1.1.4 | Detail Engineering for Installation | LS | 1
1.1.5 | Engineering for recovery of the existing SPC in J-Tube and HDD | LS | 1
1.1.6 | Perform an engineering post-lay as-built and video DVD - photographic records | LS | 1 | [5 empty] | 10%
1.2 | Optional Engineering
1.2.1 | Engineering for Complete recovery of the existing SPC | LS | 1
2 | Surveys | [7 empty] | 5%
2.1 | Pre-laid surveys | LS | 1 | [5 empty] | 50% | split in each report of requested/necessary survey
2.2 | Post-laid surveys | LS | 1 | [5 empty] | 50% | split in each report of requested/necessary survey
3 | Supply | [7 empty] | 10%
3.1 | Submarine power cable-SPC
3.1.1 | Fabrication Inspection and Control | LS | 1 | [5 empty] | 70% | Percentage according to manufacturing curve progress. Includes the full scope stated in the contract
3.1.2 | Transportation SPC and its accesories to Site (Dos Bocas - Paraíso - Tabasco - MX) from Asia | LS | 1 | [5 empty] | 20% | 100%: Arrive to México, Puerto de Dos Bocas
3.2 | Material Supply
3.2.1 | Materials required | LS | 1 | [5 empty] | 10% | 100% delivered on site for each item | Que materiales, ver items cotizados en cable
4 | Construction | [7 empty] | 70%
4.1 | Execution
4.1.1 | Mobilization (all necesarry workforce, equipment and vessel installation ready in site for installation scope) | LS | 1 | [5 empty] | 10%
4.1.2 | Installation onshore (complete scope) | LS | 1 | [5 empty] | 10% | Trenching, lying, transition boxes, release QA/QC
4.1.3 | Partial Recovery and Pull-In of Cable thru HDD | LS | 1 | [5 empty] | 10% | Execition, disposal, release QA/QC
4.1.4 | Installation of P1001 (offshore) | LS | 1 | [5 empty] | 20% | lying, buried, concrete matresses, connection in J-Tube, release QA/QC
4.1.5 | Installation of P1002 (offshore) | LS | 1 | [5 empty] | 10% | lying, buried, concrete matresses, connections in J-Tube, QA/QC
4.1.6 | Connections/ Tie ins P1001 | LS | 1 | [5 empty] | 5% | terminals and, assembly, connection of FO, release QA/QC
4.1.7 | Precommisioning (including test) P1001 | LS | 1 | [5 empty] | 10% | TBD
4.1.8 | Assistance for comissioning P1001 | LS | 1 | [5 empty] | 5% | TBD
4.1.9 | Connections/ Tie ins P1002 | LS | 1 | [5 empty] | 3% | terminals and, assembly, connection of FO
4.1.10 | Precommisioning (including test) P1002 | LS | 1 | [5 empty] | 5% | TBD
4.1.11 | Assistance for comissioning P1002 | LS | 1 | [5 empty] | 2% | TBD
4.1.12 | Demobilization | LS | 1 | [5 empty] | 5% | TBD
4.1.13 | Onshore disposal of existing umbilical (partial) | LS | 1 | [5 empty] | 5% | TBD
4.2 | Optional Execution
4.2.1 | Optional - Complete recovery of the existing SPC | gl. | N/A
5 | Completion of scope | [7 empty] | 5%
5.1 | Data books and completion scope of works | LS | 1 | [5 empty] | 100% | Approved by Company
| TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 100%
Add concepts, if necessary, to include the entire scope of works.
Note on S25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Son todos los mat indicados en: 61656-523-MTQ-0002

## UNIT PRICE QUOTE FORM
UNIT PRICE QUOTE FORM
Item | Description | Unit | Estimated Quantity | Materials & Equipment | Manpower |  | Construcion Equipment | Total
|  |  |  | USD | HH | USD | USD | USD
1 | Indirect Costs
1.1 | Project General Management | Hour
1.2 | Procurement Management | Hour
1.3 | Technical Yard Office | Hour
1.4 | Precommissioning Site Assistance Onshore | day
1.5 | Precommissioning Site Assistance Offshore | day
1.6 | Commissioning Site Assistance Onshore | day
1.7 | Commissioning Site Assistance Offshore | day
1.8 | Start Up Site Assistance | day
2 | Vessels prices (includding Fuel, Lubes, maintenance, and subsistence) |  | Operation rate | Stand By rate
2.1 | Personnel Transport – Crew Boats | day
2.2 | Logistics Supply – Supply Vessels | day | Operation | Std by
2.3 | Lay Vessel – Cable lay vessel | day | Operation | Std by
2.4 | Survey vessel | day | Operation | Std by
3 | Other requested budgetary prices
3.1 | Concret Matress for offshore crossing | ea
3.2 | ROV | Hour
3.3 | Diving team and equipment | Hour
3.4 | Mark up fee for Reimbursables | %